## Foglio1
Test | Start Date | Day to Complete
DB [DataBase (Save Tournament)] | 2018-02-26 | 7
GUI [Graphical Use Interface] | 2018-02-26 | 7 | 43157
Create Tournaments | 2018-03-05 | 14
Players Management | 2018-03-05 | 14
Teams Management | 2018-03-05 | 14
Matches Management | 2018-03-19 | 35
Results Management | 2018-04-23 | 35