## Foglio1
Tasks | ES | LS | EF | LF | SLACK
DB [DataBase (Save Tournament)] | 0 | 0 | 7 | 7 | 0
GUI [Graphical Use Interface] | 0 | 0 | 7 | 7 | 0
Create Tournaments | 7 | 7 | 2 | 9 | 0
Players Management | 7 | 7 | 2 | 9 | 0
Teams Management | 7 | 7 | 2 | 9 | 0
Matches Management | 7 | 7 | 5 | 12 | 0
Results Management | 12 | 12 | 5 | 17 | 0
DB [DataBase (Save Tournament)] |  |  | GUI [Graphical Use Interface] |  |  | Create Tournaments |  | Matches Management |  | Results Management
Start Day: 26/02/2018 | ID: 1 |  | Start Day: 26/02/2018 | ID: 2 |  | Start Day: | ID: 3 | Start Day: | ID: 6 | Start Day: | ID: 7
Finish Day: | Dur: 7 |  | Finish Day: | Dur: 7 |  | Finish Day: | Dur: 2 | Finish Day: | Dur: 5 | Finish Day: | Dur: 5
Players Management
[6 empty] | Start Day: | ID: 4
[6 empty] | Finish Day: | Dur: 2
Teams Management
[6 empty] | Start Day: | ID: 5
[6 empty] | Finish Day: | Dur: 2