## Foglio1
Test | Start Date | Days to Complete
DB [DataBase (Save Tournament)] | 2018-02-26 | 7
GUI [Graphical Use Interface] | 2018-02-26 | 7 | 43157
Create Tournaments | 2018-03-05 | 2
Players Management | 2018-03-05 | 2
Teams Management | 2018-03-05 | 2
Matches Management | 2018-03-05 | 5
Results Management | 2018-03-12 | 5